## Official Roadmap
GSS - FS/CC | Global | Americas | Otis NA | 2019-05-01 | 2020-03-31 | 17 | 27 | #VALUE! | #VALUE!
GSS - FS/CC | Global | EMEA | Portugal | 2020-01-01 | 2020-06-30 | 25 | 30 | #VALUE! | #VALUE!
GSS - FS/CC | Global | EMEA | Spain | 2020-01-01 | 2020-06-30 | 25 | 30 | #VALUE! | #VALUE!
GSS - FS/CC | Global | EMEA | Switzerland | 2020-01-01 | 2020-06-30 | 25 | 30 | #VALUE! | #VALUE!
GSS - FS/CC | Global | APAC | Hong Kong | 2020-07-01 | 2020-12-31 | 31 | 36 | #VALUE! | #VALUE!
GSS - FS/CC | Global | EMEA | France | 2020-07-01 | 2020-12-31 | 31 | 36 | #VALUE! | #VALUE!
GSS - FS/CC | Global | APAC | Japan | 2021-01-01 | 2021-06-30 | 37 | 42 | #VALUE! | #VALUE!
GSS - FS/CC | Global | APAC | Korea | 2021-01-01 | 2021-06-30 | 37 | 42 | #VALUE! | #VALUE!
GSS - FS/CC | Global | EMEA | Germany | 2021-01-01 | 2021-06-30 | 37 | 42 | #VALUE! | #VALUE!
GSS - FS/CC | Global | EMEA | Italy | 2021-01-01 | 2021-06-30 | 37 | 42 | #VALUE! | #VALUE!
GSS - FS/CC | Global | EMEA | UK | 2021-01-01 | 2021-06-30 | 37 | 42 | #VALUE! | #VALUE!
GSS - Sales | Global | Americas | Otis NA | 2018-09-01 | 2019-04-30 | 9 | 16 | #VALUE! | #VALUE!
GSS - Sales | Global | EMEA | Portugal | 2018-09-01 | 2019-04-30 | 9 | 16 | #VALUE! | #VALUE!
GSS - Sales | Global | EMEA | Switzerland | 2018-09-01 | 2019-04-30 | 9 | 16 | #VALUE! | #VALUE!
GSS - Sales | Global | EMEA | France | 2019-04-01 | 2019-09-30 | 16 | 21 | #VALUE! | #VALUE!
GSS - Sales | Global | EMEA | Spain | 2019-04-01 | 2019-09-30 | 16 | 21 | #VALUE! | #VALUE!
GSS - Sales | Global | APAC | Hong Kong | 2019-07-01 | 2019-12-31 | 19 | 24 | #VALUE! | #VALUE!
GSS - Sales | Global | APAC | Japan | 2020-07-01 | 2020-12-31 | 31 | 36 | #VALUE! | #VALUE!
GSS - Sales | Global | APAC | Korea | 2020-07-01 | 2020-12-31 | 31 | 36 | #VALUE! | #VALUE!
GSS - Sales | Global | EMEA | Germany | 2020-07-01 | 2020-12-31 | 31 | 36 | #VALUE! | #VALUE!
GSS - Sales | Global | EMEA | Italy | 2020-07-01 | 2020-12-31 | 31 | 36 | #VALUE! | #VALUE!
GSS - Sales | Global | EMEA | UK | 2020-07-01 | 2020-12-31 | 31 | 36 | #VALUE! | #VALUE!
NE - CRM | Global | EMEA | Germany | 2019-04-01 | 2019-12-31 | 16 | 24 | #VALUE! | #VALUE!
NE - CRM | Global | APAC | India | 2019-04-01 | 2019-12-31 | 16 | 24 | #VALUE! | #VALUE!
NE - CRM | Global | Americas | Otis NA - Dallas | 2019-04-01 | 2019-06-30 | 16 | 18 | #VALUE! | #VALUE!
NE - CRM | Global | Americas | Otis NA - Fort Worth | 2019-04-01 | 2019-06-30 | 16 | 18 | #VALUE! | #VALUE!
NE - CRM | Global | Americas | Otis NA - Washington D.C. | 2019-04-01 | 2019-06-30 | 16 | 18 | #VALUE! | #VALUE!
NE - CRM | Global | EMEA | Turkey | 2019-04-01 | 2019-06-30 | 16 | 18 | #VALUE! | #VALUE!
NE - CRM | Global | Americas | NAA | 2019-07-01 | 2019-12-31 | 19 | 24 | #VALUE! | #VALUE!
NE - CRM | Global | EMEA | France | 2020-01-01 | 2020-01-31 | 25 | 25 | #VALUE! | #VALUE!
NE - CRM | Global | APAC | SE Asia | 2020-02-01 | 2020-02-29 | 26 | 26 | #VALUE! | #VALUE!
NE - CRM | Global | EMEA | Spain | 2020-02-01 | 2020-02-29 | 26 | 26 | #VALUE! | #VALUE!
NE - CRM | Global | APAC | Australia | 2020-03-01 | 2020-03-31 | 27 | 27 | #VALUE! | #VALUE!
NE - CRM | Global | EMEA | Russia | 2020-04-01 | 2020-04-30 | 28 | 28 | #VALUE! | #VALUE!
NE - CRM | Global | EMEA | Italy | 2020-06-01 | 2020-06-30 | 30 | 30 | #VALUE! | #VALUE!
NE - CRM | Global | APAC | Korea | 2020-06-01 | 2020-06-30 | 30 | 30 | #VALUE! | #VALUE!
NE - CRM | Global | APAC | OCL | 2020-07-01 | 2021-03-31 | 31 | 39 | #VALUE! | #VALUE!
NE - CRM | Global | APAC | Otis Electric | 2020-07-01 | 2021-03-31 | 31 | 39 | #VALUE! | #VALUE!
NE - CRM | Global | EMEA | UK | 2021-05-01 | 2021-05-31 | 41 | 41 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | Americas | Otis NA | 2019-01-01 | 2019-12-31 | 13 | 24 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | APAC | Australia | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | Americas | Canada | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | EMEA | France | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | EMEA | Germany | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | APAC | India | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | APAC | Indonesia | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | APAC | Korea | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | APAC | Malaysia | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | Americas | Mexico | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | APAC | Singapore | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | EMEA | Spain | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | APAC | Thailand | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | EMEA | UK | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Customer Dashboard | Global | APAC | Vietnam | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
NE - Integrated Architect Asst. | Global | Americas | Canada | 2018-10-01 | 2019-06-30 | 10 | 18 | #VALUE! | #VALUE!
NE - Integrated Architect Asst. | Global | EMEA | France | 2018-10-01 | 2019-06-30 | 10 | 18 | #VALUE! | #VALUE!
NE - Integrated Architect Asst. | Global | EMEA | Germany | 2018-10-01 | 2019-06-30 | 10 | 18 | #VALUE! | #VALUE!
NE - Integrated Architect Asst. | Global | APAC | Hong Kong | 2018-10-01 | 2019-06-30 | 10 | 18 | #VALUE! | #VALUE!
NE - Integrated Architect Asst. | Global | APAC | Indonesia | 2018-10-01 | 2019-06-30 | 10 | 18 | #VALUE! | #VALUE!
NE - Integrated Architect Asst. | Global | APAC | Malaysia | 2018-10-01 | 2019-06-30 | 10 | 18 | #VALUE! | #VALUE!
NE - Integrated Architect Asst. | Global | APAC | OCL | 2018-10-01 | 2019-06-30 | 10 | 18 | #VALUE! | #VALUE!
NE - Integrated Architect Asst. | Global | Americas | Otis NA | 2018-10-01 | 2019-06-30 | 10 | 18 | #VALUE! | #VALUE!
NE - Integrated Architect Asst. | Global | APAC | Singapore | 2018-10-01 | 2019-06-30 | 10 | 18 | #VALUE! | #VALUE!
NE - Integrated Architect Asst. | Global | APAC | Taiwan | 2018-10-01 | 2019-06-30 | 10 | 18 | #VALUE! | #VALUE!
NE - Integrated Architect Asst. | Global | APAC | Thailand | 2018-10-01 | 2019-06-30 | 10 | 18 | #VALUE! | #VALUE!
NE - Integrated Architect Asst. | Global | EMEA | UK | 2018-10-01 | 2019-06-30 | 10 | 18 | #VALUE! | #VALUE!
NE - Otis.com | Global | EMEA | Turkey | 2018-09-01 | 2018-10-31 | 9 | 10 | #VALUE! | #VALUE!
NE - Otis.com | Global | APAC | Japan | 2018-09-01 | 2018-10-31 | 9 | 10 | #VALUE! | #VALUE!
NE - Otis.com | Global | Americas | Latin America | 2018-09-01 | 2018-10-31 | 9 | 10 | #VALUE! | #VALUE!
NE - Otis.com | Global | EMEA | EMEA All | 2018-10-01 | 2018-12-31 | 10 | 12 | #VALUE! | #VALUE!
NE - Otis.com | Global | APAC | Hong Kong | 2018-10-01 | 2018-11-30 | 10 | 11 | #VALUE! | #VALUE!
NE - Otis.com | Global | APAC | Taiwan | 2018-10-01 | 2018-11-30 | 10 | 11 | #VALUE! | #VALUE!
NE - Post Award Field App | Global | Americas | NAA | 2019-01-01 | 2019-09-30 | 13 | 21 | #VALUE! | #VALUE!
NE - Post Award Field App | Global | EMEA | France | 2019-01-01 | 2019-09-30 | 13 | 21 | #VALUE! | #VALUE!
NE - Post Award Field App | Global | EMEA | Germany | 2019-01-01 | 2019-09-30 | 13 | 21 | #VALUE! | #VALUE!
NE - Post Award Field App | Global | EMEA | Spain | 2019-01-01 | 2019-09-30 | 13 | 21 | #VALUE! | #VALUE!
NE - Post Award Field App | Global | EMEA | UK | 2019-01-01 | 2019-09-30 | 13 | 21 | #VALUE! | #VALUE!
NE - Post Award Field App | Global | APAC | Australia | 2019-04-01 | 2019-12-31 | 16 | 24 | #VALUE! | #VALUE!
NE - Post Award Field App | Global | APAC | India | 2019-04-01 | 2019-12-31 | 16 | 24 | #VALUE! | #VALUE!
NE - Post Award Field App | Global | APAC | Korea | 2019-04-01 | 2019-12-31 | 16 | 24 | #VALUE! | #VALUE!
NE - Post Award Field App | Global | APAC | SE Asia | 2019-04-01 | 2019-12-31 | 16 | 24 | #VALUE! | #VALUE!
NE - Sales Hub | Global | Americas | Brazil | 2018-11-01 | 2019-03-31 | 11 | 15 | #VALUE! | #VALUE!
NE - Sales Hub | Global | Americas | NAA | 2018-11-01 | 2018-12-31 | 11 | 12 | #VALUE! | #VALUE!
NE - Sales Hub | Global | EMEA | France | 2018-12-01 | 2019-06-30 | 12 | 18 | #VALUE! | #VALUE!
NE - Sales Hub | Global | EMEA | Germany | 2018-12-01 | 2019-06-30 | 12 | 18 | #VALUE! | #VALUE!
NE - Sales Hub | Global | APAC | OCL | 2018-12-01 | 2019-01-31 | 12 | 13 | #VALUE! | #VALUE!
NE - Sales Hub | Global | EMEA | Spain | 2018-12-01 | 2019-06-30 | 12 | 18 | #VALUE! | #VALUE!
NE - Sales Hub | Global | APAC | India | 2019-01-01 | 2019-03-31 | 13 | 15 | #VALUE! | #VALUE!
NE - Sales Hub | Global | APAC | Otis Electric | 2019-01-01 | 2019-03-31 | 13 | 15 | #VALUE! | #VALUE!
NE - Sales Hub | Global | APAC | Korea | 2019-04-01 | 2019-06-30 | 16 | 18 | #VALUE! | #VALUE!
NE - Sales Hub | Global | APAC | SE Asia | 2019-04-01 | 2019-06-30 | 16 | 18 | #VALUE! | #VALUE!
Otis ONE - Data Solution | Global | APAC | China | 2019-01-01 | 2019-05-31 | 13 | 17 | #VALUE! | #VALUE!
Otis ONE - Data Solution | Global | EMEA | France | 2019-01-01 | 2019-05-31 | 13 | 17 | #VALUE! | #VALUE!
Otis ONE - Data Solution | Global | Americas | Otis NA | 2019-03-01 | 2019-07-31 | 15 | 19 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | Americas | Otis NA | 2018-06-01 | 2019-02-28 | 6 | 14 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | EMEA | Austria | 2018-08-01 | 2019-02-28 | 8 | 14 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | EMEA | France | 2018-08-01 | 2019-02-28 | 8 | 14 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | EMEA | Germany | 2018-08-01 | 2019-02-28 | 8 | 14 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | APAC | Hong Kong | 2018-08-01 | 2019-03-31 | 8 | 15 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | APAC | Singapore | 2018-08-01 | 2019-03-31 | 8 | 15 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | APAC | China | 2018-11-01 | 2019-03-31 | 11 | 15 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | APAC | Japan | 2019-03-01 | 2019-05-31 | 15 | 17 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | APAC | Korea | 2019-03-01 | 2019-05-31 | 15 | 17 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | EMEA | Spain | 2019-03-01 | 2019-05-31 | 15 | 17 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | EMEA | UK | 2019-03-01 | 2019-05-31 | 15 | 17 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | EMEA | Belgium | 2019-05-01 | 2019-07-31 | 17 | 19 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | EMEA | Luxemburg | 2019-05-01 | 2019-07-31 | 17 | 19 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | EMEA | Netherlands | 2019-05-01 | 2019-07-31 | 17 | 19 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | EMEA | Portugal | 2019-07-01 | 2019-09-30 | 19 | 21 | #VALUE! | #VALUE!
Otis ONE - Multimedia | Global | EMEA | Switzerland | 2019-07-01 | 2019-09-30 | 19 | 21 | #VALUE! | #VALUE!
SVC - Customer Portal | Global | APAC | Hong Kong (ONE Pilots) | 2018-11-01 | 2018-11-30 | 11 | 11 | #VALUE! | #VALUE!
SVC - Customer Portal | Global | Americas | Otis NA - West Palm Beach | 2018-11-01 | 2018-11-30 | 11 | 11 | #VALUE! | #VALUE!
SVC - Customer Portal | Global | EMEA | Austria (ONE Pilots) | 2018-12-01 | 2018-12-31 | 12 | 12 | #VALUE! | #VALUE!
SVC - Customer Portal | Global | EMEA | France (ONE Pilots) | 2018-12-01 | 2018-12-31 | 12 | 12 | #VALUE! | #VALUE!
SVC - Customer Portal | Global | EMEA | Germany (ONE Pilots) | 2018-12-01 | 2018-12-31 | 12 | 12 | #VALUE! | #VALUE!
SVC - Customer Portal | Global | APAC | Otis Electric (ONE Pilots) | 2018-12-01 | 2018-12-31 | 12 | 12 | #VALUE! | #VALUE!
SVC - Customer Portal | Global | Americas | Otis NA - One Pilots | 2018-12-01 | 2018-12-31 | 12 | 12 | #VALUE! | #VALUE!
SVC - Customer Portal | Global | APAC | Singapore (ONE Pilots) | 2018-12-01 | 2018-12-31 | 12 | 12 | #VALUE! | #VALUE!
JDE | Global | APAC | Hong Kong | 2018-01-01 | 2018-01-31 | 1 | 1 | #VALUE! | #VALUE!
JDE | Global | EMEA | South Africa | 2018-01-01 | 2018-01-31 | 1 | 1 | #VALUE! | #VALUE!
JDE | Global | APAC | Malaysia | 2018-01-01 | 2018-02-28 | 1 | 2 | #VALUE! | #VALUE!
JDE | Global | APAC | Jpn/Schindler | 2018-01-01 | 2018-03-31 | 1 | 3 | #VALUE! | #VALUE!
JDE | Global | Americas | Otis NA Ph.1 | 2018-01-01 | 2018-05-31 | 1 | 5 | #VALUE! | #VALUE!
JDE | Global | APAC | India | 2018-01-01 | 2018-07-31 | 1 | 7 | #VALUE! | #VALUE!
JDE | Global | APAC | Fiji/Samoa | 2018-01-01 | 2018-08-31 | 1 | 8 | #VALUE! | #VALUE!
JDE | Global | Americas | Chile | 2018-01-01 | 2018-09-30 | 1 | 9 | #VALUE! | #VALUE!
JDE | Global | APAC | Otis Electric | 2018-01-01 | 2019-01-31 | 1 | 13 | #VALUE! | #VALUE!
JDE | Global | Americas | Otis NA Ph.2 | 2018-06-01 | 2019-02-28 | 6 | 14 | #VALUE! | #VALUE!
JDE | Global | Americas | OSC | 2018-11-01 | 2019-09-30 | 11 | 21 | #VALUE! | #VALUE!
JDE | Global | APAC | OCL | 2019-01-01 | 2019-08-31 | 13 | 20 | #VALUE! | #VALUE!
JDE | Global | EMEA | Austria | 2019-01-01 | 2020-01-31 | 13 | 25 | #VALUE! | #VALUE!
JDE | Global | EMEA | UK & Ireland | 2019-04-01 | 2020-04-30 | 16 | 28 | #VALUE! | #VALUE!
JDE | Global | EMEA | France | 2019-04-01 | 2020-05-31 | 16 | 29 | #VALUE! | #VALUE!
JDE | Global | EMEA | UAE/Qatar/MET | 2019-05-01 | 2020-01-31 | 17 | 25 | #VALUE! | #VALUE!
JDE | Global | EMEA | Germany | 2019-07-01 | 2020-05-31 | 19 | 29 | #VALUE! | #VALUE!
JDE | Global | Americas | Otis NA Ph.3 | 2019-09-01 | 2020-04-30 | 21 | 28 | #VALUE! | #VALUE!
JDE | Global | EMEA | CEAM | 2019-10-01 | 2020-11-30 | 22 | 35 | #VALUE! | #VALUE!
JDE | Global | EMEA | Denmark | 2019-10-01 | 2020-02-29 | 22 | 26 | #VALUE! | #VALUE!
JDE | Global | APAC | Japan | 2019-10-01 | 2020-07-31 | 22 | 31 | #VALUE! | #VALUE!
JDE | Global | EMEA | Saudi Arabia/Bahrain | 2019-11-01 | 2020-05-31 | 23 | 29 | #VALUE! | #VALUE!
JDE | Global | EMEA | Portugal | 2020-01-01 | 2020-08-31 | 25 | 32 | #VALUE! | #VALUE!
JDE | Global | EMEA | Netherlands | 2020-01-01 | 2020-12-31 | 25 | 36 | #VALUE! | #VALUE!
JDE | Global | APAC | Taiwan | 2020-02-01 | 2020-07-31 | 26 | 31 | #VALUE! | #VALUE!
JDE | Global | EMEA | Russia | 2020-03-01 | 2020-11-30 | 27 | 35 | #VALUE! | #VALUE!
JDE | Global | Americas | Brazil | 2020-04-01 | 2021-01-31 | 28 | 37 | #VALUE! | #VALUE!
JDE | Global | EMEA | Italy | 2020-04-01 | 2021-03-31 | 28 | 39 | #VALUE! | #VALUE!
JDE | Global | EMEA | Switzerland | 2020-04-01 | 2020-12-31 | 28 | 36 | #VALUE! | #VALUE!
JDE | Global | APAC | Korea | 2020-04-01 | 2021-01-31 | 28 | 37 | #VALUE! | #VALUE!
JDE | Global | EMEA | Poland | 2020-06-01 | 2020-12-31 | 30 | 36 | #VALUE! | #VALUE!
JDE | Global | EMEA | Belgium/Lux | 2020-07-01 | 2020-11-30 | 31 | 35 | #VALUE! | #VALUE!
JDE | Global | EMEA | France EPC | 2020-09-01 | 2021-09-30 | 33 | 45 | #VALUE! | #VALUE!
JDE | Global | EMEA | Spain | 2020-10-01 | 2021-06-30 | 34 | 42 | #VALUE! | #VALUE!
JDE | Global | EMEA | Sweden | 2020-11-01 | 2021-06-30 | 35 | 42 | #VALUE! | #VALUE!
JDE | Global | Americas | Central America | 2021-01-01 | 2021-03-31 | 37 | 39 | #VALUE! | #VALUE!
JDE | Global | EMEA | Estonia | 2021-01-01 | 2021-03-31 | 37 | 39 | #VALUE! | #VALUE!
JDE | Global | EMEA | Latvia | 2021-01-01 | 2021-03-31 | 37 | 39 | #VALUE! | #VALUE!
JDE | Global | APAC | Supriya/TRIO | 2021-01-01 | 2021-04-30 | 37 | 40 | #VALUE! | #VALUE!
JDE | Global | EMEA | Ukraine | 2021-01-01 | 2021-03-31 | 37 | 39 | #VALUE! | #VALUE!
JDE | Global | Americas | Argentina | 2021-01-01 | 2021-04-30 | 37 | 40 | #VALUE! | #VALUE!
JDE | Global | EMEA | Kenya | 2021-01-01 | 2021-05-31 | 37 | 41 | #VALUE! | #VALUE!
JDE | Global | EMEA | Bulgaria | 2021-01-01 | 2021-06-30 | 37 | 42 | #VALUE! | #VALUE!
JDE | Global | EMEA | Cz Rep/Slovakia | 2021-01-01 | 2021-06-30 | 37 | 42 | #VALUE! | #VALUE!
JDE | Global | EMEA | Hungary | 2021-01-01 | 2021-06-30 | 37 | 42 | #VALUE! | #VALUE!
JDE | Global | Americas | Colombia | 2021-01-01 | 2021-08-31 | 37 | 44 | #VALUE! | #VALUE!
JDE | Global | EMEA | Greece/Cyprus/Balkins | 2021-01-01 | 2021-08-31 | 37 | 44 | #VALUE! | #VALUE!
JDE | Global | EMEA | Egypt | 2021-01-01 | 2021-11-30 | 37 | 47 | #VALUE! | #VALUE!
JDE - RevRec | Global | Americas | Mexico | 2018-07-01 | 2018-10-31 | 7 | 10 | #VALUE! | #VALUE!
JDE - RevRec | Global | APAC | Otis Electric | 2018-07-01 | 2018-12-31 | 7 | 12 | #VALUE! | #VALUE!
JDE - RevRec | Global | Americas | NAA | 2018-10-01 | 2019-03-31 | 10 | 15 | #VALUE! | #VALUE!
JDE - RevRec | Global | APAC | India | 2019-03-01 | 2019-08-31 | 15 | 20 | #VALUE! | #VALUE!
JDE - RevRec | Global | APAC | Singapore | 2019-03-01 | 2019-08-31 | 15 | 20 | #VALUE! | #VALUE!
JDE - RevRec | Global | APAC | Australasia | 2019-08-01 | 2019-12-31 | 20 | 24 | #VALUE! | #VALUE!
JDE - RevRec | Global | APAC | Hong Kong | 2019-08-01 | 2019-12-31 | 20 | 24 | #VALUE! | #VALUE!
JDE - RevRec | Global | APAC | Jpn/Schindler | 2019-08-01 | 2019-12-31 | 20 | 24 | #VALUE! | #VALUE!
JDE - RevRec | Global | APAC | Malaysia | 2019-08-01 | 2019-12-31 | 20 | 24 | #VALUE! | #VALUE!
JDE - RevRec | Global | EMEA | Finland | 2019-12-01 | 2020-05-31 | 24 | 29 | #VALUE! | #VALUE!
JDE - RevRec | Global | APAC | Indonesia | 2019-12-01 | 2020-04-30 | 24 | 28 | #VALUE! | #VALUE!
JDE - RevRec | Global | EMEA | Knutsen | 2019-12-01 | 2020-05-31 | 24 | 29 | #VALUE! | #VALUE!
JDE - RevRec | Global | EMEA | Norway | 2019-12-01 | 2020-05-31 | 24 | 29 | #VALUE! | #VALUE!
JDE - RevRec | Global | EMEA | South Africa | 2019-12-01 | 2020-05-31 | 24 | 29 | #VALUE! | #VALUE!
JDE - RevRec | Global | APAC | Thailand | 2019-12-01 | 2020-04-30 | 24 | 28 | #VALUE! | #VALUE!
JDE - RevRec | Global | APAC | Vietnam | 2019-12-01 | 2020-04-30 | 24 | 28 | #VALUE! | #VALUE!
JDE - RevRec | Global | EMEA | Morocco | 2020-04-01 | 2020-09-30 | 28 | 33 | #VALUE! | #VALUE!
JDE - RevRec | Global | EMEA | Romania | 2020-04-01 | 2020-09-30 | 28 | 33 | #VALUE! | #VALUE!
JDE - RevRec | Global | EMEA | Turkey | 2020-04-01 | 2020-09-30 | 28 | 33 | #VALUE! | #VALUE!
JDE - RevRec | Global | Americas | Chile | 2020-05-01 | 2020-09-30 | 29 | 33 | #VALUE! | #VALUE!
JDE - RevRec | Global | Americas | Uruguay | 2020-05-01 | 2020-09-30 | 29 | 33 | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[8 empty] | #VALUE! | #VALUE!
[10 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[10 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[10 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## WIPRoadmap
Legend | [7 empty] | `` |  | WIP Implementation Roadmap (Jan '18 - Dec '23)
Manufacturing / Engineering
Call Center
Service Sales
Field Service
Marketing | Global / Local | Region | Business | Start Date | End Date |  |  | Res1 | Res2 | Year | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023
Finance | [9 empty] | Quarter | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Information Technology | [9 empty] | Month | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72
Column1 | Column113 | Column112 | Column111 | Column1113 | Column1112 | Column11122 | Column11123 | Column114 | Column115 | Column110 | Column2 | Column310 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34 | Column35 | Column36 | Column37 | Column38 | Column39 | Column40 | Column41 | Column42 | Column43 | Column44 | Column45 | Column46 | Column47 | Column48 | Column49 | Column50 | Column51 | Column52 | Column53 | Column54 | Column55 | Column56 | Column57 | Column58 | Column59 | Column60 | Column61 | Column62 | Column63 | Column64 | Column65 | Column66 | Column67 | Column68 | Column69 | Column70 | Column71 | Column72 | Column73
GSS - FS/CC | Global | Americas | Otis NA | 2019-01-01 | 2020-03-31 | 13 | 27 | FService | CallC
GSS - FS/CC | Global | EMEA | Portugal | 2020-01-01 | 2020-09-30 | 25 | 33 | FService | CallC
GSS - FS/CC | Global | EMEA | Germany | 2020-04-01 | 2020-12-31 | 28 | 36 | FService | CallC
GSS - FS/CC | Global | EMEA | Italy | 2020-04-01 | 2020-12-31 | 28 | 36 | FService | CallC
GSS - FS/CC | Global | EMEA | UK | 2020-04-01 | 2020-12-31 | 28 | 36 | FService | CallC
GSS - FS/CC | Global | EMEA | France | 2020-07-01 | 2021-03-31 | 31 | 39 | FService | CallC
GSS - FS/CC | Global | APAC | Hong Kong | 2020-07-01 | 2020-12-31 | 31 | 36 | FService | CallC
GSS - FS/CC | Global | EMEA | Switzerland | 2020-07-01 | 2020-12-31 | 31 | 36 | FService | CallC
GSS - FS/CC | Global | APAC | Japan | 2021-01-01 | 2021-06-30 | 37 | 42 | FService | CallC
GSS - FS/CC | Global | APAC | Korea | 2021-01-01 | 2021-06-30 | 37 | 42 | FService | CallC
GSS - FS/CC | Global | EMEA | Spain | 2021-07-01 | 2022-03-31 | 43 | 51 | FService | CallC
GSS - Sales | Global | Americas | Otis NA | 2019-01-01 | 2019-06-30 | 13 | 18 | SSales | SSales
GSS - Sales | Global | EMEA | Portugal | 2019-02-01 | 2019-05-31 | 14 | 17 | SSales | SSales
GSS - Sales | Global | EMEA | Switzerland | 2019-02-01 | 2019-05-31 | 14 | 17 | SSales | SSales
GSS - Sales | Global | APAC | Hong Kong | 2019-07-01 | 2019-12-31 | 19 | 24 | SSales | SSales
GSS - Sales | Global | EMEA | France | 2020-01-01 | 2020-09-30 | 25 | 33 | SSales | SSales
GSS - Sales | Global | EMEA | Germany | 2020-04-01 | 2020-09-30 | 28 | 33 | SSales | SSales
GSS - Sales | Global | EMEA | Italy | 2020-04-01 | 2020-09-30 | 28 | 33 | SSales | SSales
GSS - Sales | Global | EMEA | UK | 2020-04-01 | 2020-09-30 | 28 | 33 | SSales | SSales
GSS - Sales | Global | EMEA | Spain | 2021-01-01 | 2021-06-30 | 37 | 42 | SSales | SSales
GSS - Sales | Global | APAC | Korea | 2021-02-01 | 2021-10-31 | 38 | 46 | SSales | SSales
GSS - Sales | Global | APAC | Japan | 2022-02-01 | 2022-10-31 | 50 | 58 | SSales | SSales
JDE | Global | APAC | Hong Kong | 2018-01-01 | 2018-01-31 | 1 | 1 | Fin | IT
JDE | Global | EMEA | South Africa | 2018-01-01 | 2018-01-31 | 1 | 1 | Fin | IT
JDE | Global | APAC | Malaysia | 2018-01-01 | 2018-02-28 | 1 | 2 | Fin | IT
JDE | Global | APAC | Jpn/Schindler | 2018-01-01 | 2018-03-31 | 1 | 3 | Fin | IT
JDE | Global | Americas | Otis NA Ph.1 | 2018-01-01 | 2018-05-31 | 1 | 5 | Fin | IT
JDE | Global | APAC | India | 2018-01-01 | 2018-07-31 | 1 | 7 | Fin | IT
JDE | Global | APAC | Fiji/Samoa | 2018-01-01 | 2018-08-31 | 1 | 8 | Fin | IT
JDE | Global | Americas | Chile | 2018-01-01 | 2018-09-30 | 1 | 9 | Fin | IT
JDE | Global | APAC | Otis Electric | 2018-01-01 | 2019-01-31 | 1 | 13 | Fin | IT
JDE | Global | Americas | Otis NA Ph.2 | 2018-06-01 | 2019-02-28 | 6 | 14 | Fin | IT
JDE | Global | Americas | OSC | 2018-11-01 | 2019-09-30 | 11 | 21 | Fin | IT
JDE | Global | APAC | OCL | 2019-01-01 | 2019-08-31 | 13 | 20 | Fin | IT
JDE | Global | EMEA | Austria | 2019-01-01 | 2020-01-31 | 13 | 25 | Fin | IT
JDE | Global | EMEA | UK & Ireland | 2019-04-01 | 2020-04-30 | 16 | 28 | Fin | IT
JDE | Global | EMEA | France | 2019-04-01 | 2020-05-31 | 16 | 29 | Fin | IT
JDE | Global | EMEA | UAE/Qatar/MET | 2019-05-01 | 2020-01-31 | 17 | 25 | Fin | IT
JDE | Global | EMEA | Germany | 2019-07-01 | 2020-05-31 | 19 | 29 | Fin | IT
JDE | Global | Americas | Otis NA Ph.3 | 2019-09-01 | 2020-04-30 | 21 | 28 | Fin | IT
JDE | Global | EMEA | CEAM | 2019-10-01 | 2020-11-30 | 22 | 35 | Fin | IT
JDE | Global | EMEA | Denmark | 2019-10-01 | 2020-02-29 | 22 | 26 | Fin | IT
JDE | Global | APAC | Japan | 2019-10-01 | 2020-07-31 | 22 | 31 | Fin | IT
JDE | Global | EMEA | Saudi Arabia/Bahrain | 2019-11-01 | 2020-05-31 | 23 | 29 | Fin | IT
JDE | Global | EMEA | Portugal | 2020-01-01 | 2020-08-31 | 25 | 32 | Fin | IT
JDE | Global | EMEA | Netherlands | 2020-01-01 | 2020-12-31 | 25 | 36 | Fin | IT
JDE | Global | APAC | Taiwan | 2020-02-01 | 2020-07-31 | 26 | 31 | Fin | IT
JDE | Global | EMEA | Russia | 2020-03-01 | 2020-11-30 | 27 | 35 | Fin | IT
JDE | Global | Americas | Brazil | 2020-04-01 | 2021-01-31 | 28 | 37 | Fin | IT
JDE | Global | EMEA | Italy | 2020-04-01 | 2021-03-31 | 28 | 39 | Fin | IT
JDE | Global | EMEA | Switzerland | 2020-04-01 | 2020-12-31 | 28 | 36 | Fin | IT
JDE | Global | APAC | Korea | 2020-04-01 | 2021-01-31 | 28 | 37 | Fin | IT
JDE | Global | EMEA | Poland | 2020-06-01 | 2020-12-31 | 30 | 36 | Fin | IT
JDE | Global | EMEA | Belgium/Lux | 2020-07-01 | 2020-11-30 | 31 | 35 | Fin | IT
JDE | Global | EMEA | France EPC | 2020-09-01 | 2021-09-30 | 33 | 45 | Fin | IT
JDE | Global | EMEA | Spain | 2020-10-01 | 2021-06-30 | 34 | 42 | Fin | IT
JDE | Global | EMEA | Sweden | 2020-11-01 | 2021-06-30 | 35 | 42 | Fin | IT
JDE | Global | Americas | Central America | 2021-01-01 | 2021-03-31 | 37 | 39 | Fin | IT
JDE | Global | EMEA | Estonia | 2021-01-01 | 2021-03-31 | 37 | 39 | Fin | IT
JDE | Global | EMEA | Latvia | 2021-01-01 | 2021-03-31 | 37 | 39 | Fin | IT
JDE | Global | APAC | Supriya/TRIO | 2021-01-01 | 2021-04-30 | 37 | 40 | Fin | IT
JDE | Global | EMEA | Ukraine | 2021-01-01 | 2021-03-31 | 37 | 39 | Fin | IT
JDE | Global | Americas | Argentina | 2021-01-01 | 2021-04-30 | 37 | 40 | Fin | IT
JDE | Global | EMEA | Kenya | 2021-01-01 | 2021-05-31 | 37 | 41 | Fin | IT
JDE | Global | EMEA | Bulgaria | 2021-01-01 | 2021-06-30 | 37 | 42 | Fin | IT
JDE | Global | EMEA | Cz Rep/Slovakia | 2021-01-01 | 2021-06-30 | 37 | 42 | Fin | IT
JDE | Global | EMEA | Hungary | 2021-01-01 | 2021-06-30 | 37 | 42 | Fin | IT
JDE | Global | Americas | Colombia | 2021-01-01 | 2021-08-31 | 37 | 44 | Fin | IT
JDE | Global | EMEA | Greece/Cyprus/Balkins | 2021-01-01 | 2021-08-31 | 37 | 44 | Fin | IT
JDE | Global | EMEA | Egypt | 2021-01-01 | 2021-11-30 | 37 | 47 | Fin | IT
JDE - RevRec | Global | Americas | Mexico | 2018-07-01 | 2018-10-31 | 7 | 10 | Fin | Fin
JDE - RevRec | Global | APAC | Otis Electric | 2018-07-01 | 2018-12-31 | 7 | 12 | Fin | Fin
JDE - RevRec | Global | Americas | NAA | 2018-10-01 | 2019-03-31 | 10 | 15 | Fin | Fin
JDE - RevRec | Global | APAC | India | 2019-03-01 | 2019-08-31 | 15 | 20 | Fin | Fin
JDE - RevRec | Global | APAC | Singapore | 2019-03-01 | 2019-08-31 | 15 | 20 | Fin | Fin
JDE - RevRec | Global | APAC | Australasia | 2019-08-01 | 2019-12-31 | 20 | 24 | Fin | Fin
JDE - RevRec | Global | APAC | Hong Kong | 2019-08-01 | 2019-12-31 | 20 | 24 | Fin | Fin
JDE - RevRec | Global | APAC | Jpn/Schindler | 2019-08-01 | 2019-12-31 | 20 | 24 | Fin | Fin
JDE - RevRec | Global | APAC | Malaysia | 2019-08-01 | 2019-12-31 | 20 | 24 | Fin | Fin
JDE - RevRec | Global | EMEA | Finland | 2019-12-01 | 2020-05-31 | 24 | 29 | Fin | Fin
JDE - RevRec | Global | APAC | Indonesia | 2019-12-01 | 2020-04-30 | 24 | 28 | Fin | Fin
JDE - RevRec | Global | EMEA | Knutsen | 2019-12-01 | 2020-05-31 | 24 | 29 | Fin | Fin
JDE - RevRec | Global | EMEA | Norway | 2019-12-01 | 2020-05-31 | 24 | 29 | Fin | Fin
JDE - RevRec | Global | EMEA | South Africa | 2019-12-01 | 2020-05-31 | 24 | 29 | Fin | Fin
JDE - RevRec | Global | APAC | Thailand | 2019-12-01 | 2020-04-30 | 24 | 28 | Fin | Fin
JDE - RevRec | Global | APAC | Vietnam | 2019-12-01 | 2020-04-30 | 24 | 28 | Fin | Fin
JDE - RevRec | Global | EMEA | Morocco | 2020-04-01 | 2020-09-30 | 28 | 33 | Fin | Fin
JDE - RevRec | Global | EMEA | Romania | 2020-04-01 | 2020-09-30 | 28 | 33 | Fin | Fin
JDE - RevRec | Global | EMEA | Turkey | 2020-04-01 | 2020-09-30 | 28 | 33 | Fin | Fin
JDE - RevRec | Global | Americas | Chile | 2020-05-01 | 2020-09-30 | 29 | 33 | Fin | Fin
JDE - RevRec | Global | Americas | Uruguay | 2020-05-01 | 2020-09-30 | 29 | 33 | Fin | Fin
NE - CRM | Global | EMEA | Germany | 2019-04-01 | 2019-12-31 | 16 | 24 | IT | Mar
NE - CRM | Global | APAC | India | 2019-04-01 | 2019-12-31 | 16 | 24 | IT | Mar
NE - CRM | Global | Americas | Otis NA - Dallas | 2019-04-01 | 2019-06-30 | 16 | 18 | IT | Mar
NE - CRM | Global | Americas | Otis NA - Fort Worth | 2019-04-01 | 2019-06-30 | 16 | 18 | IT | Mar
NE - CRM | Global | Americas | Otis NA - Washington D.C. | 2019-04-01 | 2019-06-30 | 16 | 18 | IT | Mar
NE - CRM | Global | EMEA | Turkey | 2019-04-01 | 2019-06-30 | 16 | 18 | IT | Mar
NE - CRM | Global | Americas | NAA (rest of) | 2019-07-01 | 2019-12-31 | 19 | 24 | IT | Mar
NE - CRM | Global | EMEA | France | 2020-01-01 | 2020-01-31 | 25 | 25 | IT | Mar
NE - CRM | Global | APAC | SE Asia | 2020-02-01 | 2020-02-29 | 26 | 26 | IT | Mar
NE - CRM | Global | EMEA | Spain | 2020-02-01 | 2020-02-29 | 26 | 26 | IT | Mar
NE - CRM | Global | APAC | Australia | 2020-03-01 | 2020-03-31 | 27 | 27 | IT | Mar
NE - CRM | Global | EMEA | Russia | 2020-04-01 | 2020-04-30 | 28 | 28 | IT | Mar
NE - CRM | Global | APAC | Korea | 2020-06-01 | 2020-06-30 | 30 | 30 | IT | Mar
NE - CRM | Global | APAC | OCL | 2020-07-01 | 2021-03-31 | 31 | 39 | IT | Mar
NE - CRM | Global | APAC | Otis Electric | 2020-07-01 | 2021-03-31 | 31 | 39 | IT | Mar
NE - CRM | Global | EMEA | UK | 2021-05-01 | 2021-05-31 | 41 | 41 | IT | Mar
NE - Customer Dashboard | Global | Americas | Otis NA | 2019-01-01 | 2019-12-31 | 13 | 24 | IT | Mar
NE - Customer Dashboard | Global | APAC | Australia | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Customer Dashboard | Global | Americas | Canada | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Customer Dashboard | Global | EMEA | France | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Customer Dashboard | Global | EMEA | Germany | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Customer Dashboard | Global | APAC | India | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Customer Dashboard | Global | APAC | Indonesia | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Customer Dashboard | Global | APAC | Korea | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Customer Dashboard | Global | APAC | Malaysia | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Customer Dashboard | Global | Americas | Mexico | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Customer Dashboard | Global | APAC | Singapore | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Customer Dashboard | Global | EMEA | Spain | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Customer Dashboard | Global | APAC | Thailand | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Customer Dashboard | Global | EMEA | UK | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Customer Dashboard | Global | APAC | Vietnam | 2020-01-01 | 2020-12-31 | 25 | 36 | IT | Mar
NE - Integrated Architect Asst. | Global | Americas | Canada | 2018-10-01 | 2019-09-30 | 10 | 21 | IT | IT
NE - Integrated Architect Asst. | Global | EMEA | France | 2018-10-01 | 2019-09-30 | 10 | 21 | IT | IT
NE - Integrated Architect Asst. | Global | EMEA | Germany | 2018-10-01 | 2019-06-30 | 10 | 18 | IT | IT
NE - Integrated Architect Asst. | Global | APAC | Hong Kong | 2018-10-01 | 2019-09-30 | 10 | 21 | IT | IT
NE - Integrated Architect Asst. | Global | APAC | Indonesia | 2018-10-01 | 2019-09-30 | 10 | 21 | IT | IT
NE - Integrated Architect Asst. | Global | APAC | Malaysia | 2018-10-01 | 2019-09-30 | 10 | 21 | IT | IT
NE - Integrated Architect Asst. | Global | APAC | OCL | 2018-10-01 | 2019-09-30 | 10 | 21 | IT | IT
NE - Integrated Architect Asst. | Global | Americas | Otis NA | 2018-10-01 | 2019-09-30 | 10 | 21 | IT | IT
NE - Integrated Architect Asst. | Global | APAC | Singapore | 2018-10-01 | 2019-09-30 | 10 | 21 | IT | IT
NE - Integrated Architect Asst. | Global | APAC | Taiwan | 2018-10-01 | 2019-06-30 | 10 | 18 | IT | IT
NE - Integrated Architect Asst. | Global | APAC | Thailand | 2018-10-01 | 2019-09-30 | 10 | 21 | IT | IT
NE - Integrated Architect Asst. | Global | EMEA | UK | 2018-10-01 | 2019-09-30 | 10 | 21 | IT | IT
NE - Otis.com | Global | APAC | Japan | 2018-09-01 | 2018-10-31 | 9 | 10 | IT | IT
NE - Otis.com | Global | Americas | Latin America | 2018-09-01 | 2018-10-31 | 9 | 10 | IT | IT
NE - Otis.com | Global | EMEA | Turkey | 2018-09-01 | 2018-10-31 | 9 | 10 | IT | IT
NE - Otis.com | Global | EMEA | EMEA All | 2018-10-01 | 2018-12-31 | 10 | 12 | IT | IT
NE - Otis.com | Global | APAC | Hong Kong | 2018-10-01 | 2018-11-30 | 10 | 11 | IT | IT
NE - Otis.com | Global | APAC | Taiwan | 2018-10-01 | 2018-11-30 | 10 | 11 | IT | IT
NE - Post Award Field App | Global | EMEA | France | 2019-01-01 | 2019-09-30 | 13 | 21 | IT | FService
NE - Post Award Field App | Global | EMEA | Germany | 2019-01-01 | 2019-09-30 | 13 | 21 | IT | FService
NE - Post Award Field App | Global | Americas | NAA | 2019-01-01 | 2019-09-30 | 13 | 21 | IT | FService
NE - Post Award Field App | Global | EMEA | Spain | 2019-01-01 | 2019-09-30 | 13 | 21 | IT | FService
NE - Post Award Field App | Global | EMEA | UK | 2019-01-01 | 2019-09-30 | 13 | 21 | IT | FService
NE - Post Award Field App | Global | APAC | Australia | 2019-04-01 | 2019-12-31 | 16 | 24 | IT | FService
NE - Post Award Field App | Global | APAC | India | 2019-04-01 | 2019-12-31 | 16 | 24 | IT | FService
NE - Post Award Field App | Global | APAC | Korea | 2019-04-01 | 2019-12-31 | 16 | 24 | IT | FService
NE - Post Award Field App | Global | APAC | SE Asia | 2019-04-01 | 2019-12-31 | 16 | 24 | IT | FService
NE - Sales Hub | Global | Americas | Brazil | 2018-11-01 | 2019-03-31 | 11 | 15 | IT | Mar
NE - Sales Hub | Global | Americas | NAA | 2018-11-01 | 2018-12-31 | 11 | 12 | IT | Mar
NE - Sales Hub | Global | EMEA | France | 2018-12-01 | 2019-06-30 | 12 | 18 | IT | Mar
NE - Sales Hub | Global | EMEA | Germany | 2018-12-01 | 2019-06-30 | 12 | 18 | IT | Mar
NE - Sales Hub | Global | APAC | OCL | 2018-12-01 | 2019-01-31 | 12 | 13 | IT | Mar
NE - Sales Hub | Global | EMEA | Spain | 2018-12-01 | 2019-06-30 | 12 | 18 | IT | Mar
NE - Sales Hub | Global | APAC | India | 2019-01-01 | 2019-03-31 | 13 | 15 | IT | Mar
NE - Sales Hub | Global | APAC | Otis Electric | 2019-01-01 | 2019-03-31 | 13 | 15 | IT | Mar
NE - Sales Hub | Global | APAC | Korea | 2019-04-01 | 2019-06-30 | 16 | 18 | IT | Mar
NE - Sales Hub | Global | APAC | SE Asia | 2019-04-01 | 2019-06-30 | 16 | 18 | IT | Mar
Otis ONE - Data Solution | Global | APAC | China | 2019-01-01 | 2019-05-31 | 13 | 17 | IT | Mfg/Eng
Otis ONE - Data Solution | Global | EMEA | France | 2019-01-01 | 2019-05-31 | 13 | 17 | IT | Mfg/Eng
Otis ONE - Data Solution | Global | Americas | Otis NA | 2019-03-01 | 2019-07-31 | 15 | 19 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | Americas | Otis NA | 2018-06-01 | 2019-02-28 | 6 | 14 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | EMEA | Austria | 2018-08-01 | 2019-02-28 | 8 | 14 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | EMEA | France | 2018-08-01 | 2019-02-28 | 8 | 14 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | EMEA | Germany | 2018-08-01 | 2019-02-28 | 8 | 14 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | APAC | Hong Kong | 2018-08-01 | 2019-03-31 | 8 | 15 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | APAC | Singapore | 2018-08-01 | 2019-03-31 | 8 | 15 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | APAC | China | 2018-11-01 | 2019-03-31 | 11 | 15 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | APAC | Japan | 2019-03-01 | 2019-05-31 | 15 | 17 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | APAC | Korea | 2019-03-01 | 2019-05-31 | 15 | 17 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | EMEA | Spain | 2019-03-01 | 2019-05-31 | 15 | 17 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | EMEA | UK | 2019-03-01 | 2019-05-31 | 15 | 17 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | EMEA | Belgium | 2019-05-01 | 2019-07-31 | 17 | 19 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | EMEA | Luxemburg | 2019-05-01 | 2019-07-31 | 17 | 19 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | EMEA | Netherlands | 2019-05-01 | 2019-07-31 | 17 | 19 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | EMEA | Portugal | 2019-07-01 | 2019-09-30 | 19 | 21 | IT | Mfg/Eng
Otis ONE - Multimedia | Global | EMEA | Switzerland | 2019-07-01 | 2019-09-30 | 19 | 21 | IT | Mfg/Eng
SVC - Customer Portal | Global | APAC | Hong Kong (ONE Pilots) | 2018-11-01 | 2018-11-30 | 11 | 11 | FService | IT
SVC - Customer Portal | Global | Americas | Otis NA - West Palm Beach | 2018-11-01 | 2018-11-30 | 11 | 11 | FService | IT
SVC - Customer Portal | Global | EMEA | Austria (ONE Pilots) | 2018-12-01 | 2018-12-31 | 12 | 12 | FService | IT
SVC - Customer Portal | Global | EMEA | France (ONE Pilots) | 2018-12-01 | 2018-12-31 | 12 | 12 | FService | IT
SVC - Customer Portal | Global | EMEA | Germany (ONE Pilots) | 2018-12-01 | 2018-12-31 | 12 | 12 | FService | IT
SVC - Customer Portal | Global | APAC | Otis Electric (ONE Pilots) | 2018-12-01 | 2018-12-31 | 12 | 12 | FService | IT
SVC - Customer Portal | Global | Americas | Otis NA - One Pilots | 2018-12-01 | 2018-12-31 | 12 | 12 | FService | IT
SVC - Customer Portal | Global | APAC | Singapore (ONE Pilots) | 2018-12-01 | 2018-12-31 | 12 | 12 | FService | IT
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[8 empty] | #N/A | #N/A
[11 empty] | 1674 | 1674 | 1674 | 1674 | 1674 | 2046 | 2418 | 3348 | 3906 | 6882 | 7998 | 9858 | 12462 | 12834 | 14136 | 16740 | 17484 | 17484 | 18414 | 19158 | 19344 | 19902 | 20088 | 21390 | 24924 | 25482 | 25854 | 28458 | 28830 | 29202 | 30318 | 30318 | 30504 | 30690 | 30876 | 30876 | 33852 | 34038 | 34038 | 34038 | 34224 | 34224 | 34410 | 34410 | 34410 | 34410 | 34410 | 34410 | 34410 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596
[11 empty] | 372 | 558 | 744 | 744 | 930 | 930 | 1116 | 1302 | 1488 | 2232 | 2976 | 4650 | 5022 | 5952 | 7254 | 7254 | 8742 | 10974 | 11718 | 12276 | 15624 | 15624 | 15624 | 18042 | 18600 | 19158 | 19530 | 20646 | 21948 | 22134 | 22506 | 22692 | 24552 | 24552 | 25110 | 29202 | 29574 | 29574 | 31062 | 31434 | 31806 | 33294 | 33294 | 33666 | 33852 | 34038 | 34224 | 34224 | 34224 | 34224 | 34410 | 34410 | 34410 | 34410 | 34410 | 34410 | 34410 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596 | 34596
[11 empty] | 372 | 186 | 186 | 0 | 186 | 0 | 186 | 186 | 186 | 744 | 744 | 1674 | 372 | 930 | 1302 | 0 | 1488 | 2232 | 744 | 558 | 3348 | 0 | 0 | 2418 | 558 | 558 | 372 | 1116 | 1302 | 186 | 372 | 186 | 1860 | 0 | 558 | 4092 | 372 | 0 | 1488 | 372 | 372 | 1488 | 0 | 372 | 186 | 186 | 186 | 0 | 0 | 0 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Concurrent Projects | [7 empty] | 1674 | 1302 | 1116 | 930 | 930 | 1116 | 1488 | 2232 | 2604 | 5394 | 5766 | 6882 | 7812 | 7812 | 8184 | 9486 | 10230 | 8742 | 7440 | 7440 | 7068 | 4278 | 4464 | 5766 | 6882 | 6882 | 6696 | 8928 | 8184 | 7254 | 8184 | 7812 | 7812 | 6138 | 6324 | 5766 | 4650 | 4464 | 4464 | 2976 | 2790 | 2418 | 1116 | 1116 | 744 | 558 | 372 | 186 | 186 | 372 | 372 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D46: Need to assess & complete pre-project GL account clean-up. MS CRM field upgrade could cause resource conflict
Note on D47: END DATE TBD until iCRP assessment. April start confirmed, w/ opportunito to pullinto March based on biz resource avail./backfill. Worst case, some advanced work could tentatively start Feb-Mar. iCRP projected ~October
Note on D49: Will start some advance work in ~May, DC & CoA
Note on D52: Plan is to perform project progress review in Q2, and confirm start based on overall pgm. capacity
Note on D60: Overlap CEAM, start advance work ~6 months aftter CEAM's start

## resource_info (hidden)
|  |  |  | Region | Scope | Call Center
Call Center | 82 | 166 | 68 | EMEA | Global | Service Sales
Service Sales | 156 | 201 | 125 | APAC | Local | Field Service
Field Service | 255 | 248 | 205 | Americas |  | Marketing
Marketing | 255 | 196 | 137 |  |  | Finance
Finance | 155 | 194 | 230 |  |  | Information Technology
Information Technology | 195 | 155 | 225
[6 empty] | Call Center | Service Sales | CallC | SSales
[6 empty] | Call Center | Field Service | CallC | FService
[6 empty] | Call Center | Marketing | CallC | Mar
[6 empty] | Call Center | Finance | CallC | Fin
[6 empty] | Call Center | IT | CallC | IT
[6 empty] | Service Sales | Field Service | SSales | FService
[6 empty] | Service Sales | Marketing | SSales | Mar
[6 empty] | Service Sales | Finance | SSales | Fin
[6 empty] | Service Sales | IT | SSales | IT
[6 empty] | Field Service | Marketing | FService | Mar
[6 empty] | Field Service | Finance | FService | Fin
[6 empty] | Field Service | IT | FService | IT
[6 empty] | Marketing | Finance | Mar | Fin
[6 empty] | Marketing | IT | Mar | IT
[6 empty] | Finance | IT | Fin | IT

## ResourceSheet (hidden)
Program | Resource1 | Resource2 |  | FServ
GSS - FS/CC | FServ | FServ |  | SSales
GSS - Sales | FSales | FSales |  | Fin
JDE | Fin | Fin |  | Mar
JDE - RevRec | Fin | Fin |  | IT
NE - CRM | NES | NES |  | CallCen
NE - Customer Dashboard | NES | NES
NE - Integrated Architect Asst. | NES | NES
NE - Sales Hub | NES | NES
Otis ONE - Data Solution | IT | IT
Otis ONE - Multimedia | IT | IT
SVC - Customer Portal | IT | IT
Field Service | FService | 255 | 248 | 205
Service Sales | SSales | 156 | 201 | 125
Call Center | CallC | 82 | 166 | 68
Finance | Fin | 155 | 194 | 230
Marketing | Mar | 255 | 196 | 137
IT | IT | 195 | 155 | 225
Manufacturing / Engineering | Mfg/Eng | 151 | 233 | 176
N/A

## ProgramOverview
Program | Description | Benefits | Resource1 | R1_Commit | R1 | Resource2 | R2_Commit | R2 | Dependencies | Factors
JDE | Deployment of Otis JDE Finance Global Model, including standardization of finance system use and business processes across the businesses, integrating with applications supporting processes outside of JDE scope | 1. Replace outdated / unsupported JDE and local systems 2. Improve performance / reduce month end processing time 3. Eliminate / minimize manual & excel based processes 4. Improve business information and reporting 5. Strengthen compliance / align with global model | Finance | 50% | Fin | IT | 50% | IT | N/A | N/A
JDE - RevRec | Comply with new GAAP rules and integration of additional performance & productivity improvements | 1. Comply with new GAAP rules 2. Profit recognition is redesigned from economic contract level to unit/job level of detail 3. Loss provision redesigned to include new calculations on loss provision booking, re-estimation and reversals 4. Embedded Derivative has been automated, eliminating all manual calculations 5. Backlog Analytical Table (BAT) has been redesigned into numerous reports to allow for better | Finance | 30% | Fin | IT | 7.5% | Fin | JDE | N/A
NE - CRM | Deployment of Otis CRM Global Model, including standardization a global template and processes across the new equipment business, integrating with existing business applications (eLog, JDE and Qliksense reporting) supporting existing processes that integrate with CRM. | 1. Increase SoS, Margin & Sales (Customer relationship analytics; Improved decisions) 2. Improve Hit Rate (Opportunity tracking; focus sales efforts) 3. Increase design outreach; Increase customer visits (Visibility to sales activities; improved sales management) 4. Faster response time; increased proposal & market coverage (Mobility & streamlined internal processes; minimize wasted time) 5. Improve forecast accuracy, Managers; more time to manage (Instant reports/forecast; reduce manual effort) 6. Reduce loss of project data because of attrition (Document retention; Centralized source of truth) | IT | 100% | IT | Marketing | 100% | Mar | 1. Rollout countries must have Office 365 deployed prior to CRM deployment. 2. Rollout countries must have eLog implemented or it will not be integrated in this program. 3. Rollout countries must have JDE implemented prior to CRM deployment or integration will not be completed in this program rollout. 4. Budget is based on 3 new instances globally with no more than 12 countries. 5. Existing NE instances will be separate migration projects and is not included in the estimates provided (China, LAA). | 1. If any regional changes are identified, there will be corresponding increase in the effort and cost if approved for these changes with Global Template. This is not part of current estimates and has to be estimated separately on a case to case basis. 2. Local and GHQ resources will be used in addition to the vendor partner.
NE - Customer Dashboard | Project Status Dashboard urls are emailed to customers through CRM | 1. Allows external customers to track multiple projects in 1 place 2. Customers can visualize the installation process from contract signing through turnover 3. Simplifies reporting of milestones that are behind 4. Requires no login | IT | 100% | IT | Marketing | 50% | Mar | 1. Data lake is desired source of all date replacing the need for individual data integrations with ELOG,CRM(potentially other apps) to provide 100% of the dashboard data. | Elog data quality
NE - Sales Hub | To redesign OTIS Sales Hub site in SP2013 SharePoint and migrate existing SP2013 on-premises documents and videos to new SP2013 SharePoint site. This includes migration for 1 country and site rollout for twelve (12) countries. This will result in offering uniform experience in mobile, tab and laptop/desktop. | 1. Sales Reps will have a “one stop shop” for all sales collateral 2. Sales Reps will be able to access country specific links 3. Sales Reps can stream & download videos to present to customers 4. Entry point is via Country Insight page/Intranet 5. Sales Rep specific training | IT | 80% | IT | Marketing | 50% | Mar | N/A | N/A
NE - Post Award Field App | Build and deploy a mobile tool that takes the end user through the SIP process. Integrating with eLog to give the end user a quick and easy view into his daily activity. | 1. Automates SIP Process 2. Mobile access to eLog data (SIP, project info) 3. Mobile audits/survey 4. Mobile change/variation orders 5. Mobile documents - support | IT | 100% | IT | Field Service | 100% | FService | 1. eLog API Development | N/A
GSS - Sales | Global Service System (GSS) leverages Microsoft Dynamics 365 for service sales, call center, and field service. GSS standardize business processes and will strengthen customer relationships by providing employees the tools to provide a best-in-class customer experience. GSS integrates with other global systems and In-Country legacy systems. | 1. Decrease cancellations 2. Increase Maintenance Efficiency 3. Improve Customer Experience 4. Drive Adoption and Business Value | Service Sales | 20% | SSales | N/A | N/A | SSales | N/A | N/A
GSS - FS/CC | Global Service System (GSS) leverages Microsoft Dynamics 365 for service sales, call center, and field service. GSS standardize business processes and will strengthen customer relationships by providing employees the tools to provide a best-in-class customer experience. GSS integrates with other global systems and In-Country legacy systems. | 1. Decrease cancellations 2. Increase Maintenance Efficiency 3. Improve Customer Experience 4. Drive Adoption and Business Value | Field Service | 20% | FService | Call Center | 20% | CallC | 1.GSS Sales | 1. GSS – Sales and GSS FS/CC will be a single program after the deployment of GSS FS/CC
Otis ONE - Multimedia | OtisONE is the connected elevator solution that allows a personalized experience by making management easier, system performance better and puts relevant information at your fingertips. The value proposition is to be transparent, proactive and predictive. | 1. Real-time, predictive maintenance & advanced analytics 2. 24/7 monitoring and connection to customer service/mechanic 3. Event based, digital notification and status communications 4. Personalized service portal and apps for remote access 5. Health status dashboards, including trip/door activity 6. Proactive Customer Care Center calls for shutdowns | IT | 100% | IT | Manufacturing / Engineering | 60% | Mfg/Eng |  | 1. Field trial scheduled November - January 2. Head count approval
SVC - Customer Portal | New Otis Customer Portal to provide customers with more personalized information, proactive notifications, and transparency of services. | 1. Increase customer satisfaction and increase engagement 2. Increase sales representative efficiency 3. Reduce cancellation rates 4. Improve OtisLine efficiency 5. Improve treasury efficiency with online payments | Field Service | 20% | FService | IT | 10% | IT | 1. Otis ONE Program 2. GSS CC/FS – for some integrations 3. JDE – for some integrations | 1. Otis ONE eCAR approval 2. Pilot roll outs only defined right now. Whole country roll outs still need to be planned for 2019. 3. 2019 headcount approval
Otis ONE - Data Solution | OtisONE is the connected elevator solution that allows a personalized experience by making management easier, system performance better and puts relevant information at your fingertips. The value proposition is to be transparent, proactive and predictive. | 1. Real-time, predictive maintenance & advanced analytics 2. 24/7 monitoring and connection to customer service/mechanic 3. Event based, digital notification and status communications 4. Personalized service portal and apps for remote access 5. Health status dashboards, including trip/door activity 6. Proactive Customer Care Center calls for shutdowns 7. Emergency calls via digital voice/data connection | IT | 100% | IT | Manufacturing / Engineering | 60% | Mfg/Eng |  | 1. Field trial in progress 2. Head count approval
NE - Integrated Architect Asst. |  |  | IT |  | IT | N/A |  | IT
NE - Otis.com |  | We now have a modern, professional face to the world to launch the New Otis and attract new customers through digital marketing efforts | IT |  | IT | N/A |  | IT | Deployments completed 12/12/18

## Color
Project | Project Code | Region | Region Code | Resource | Resource code
JDE |  | Americas |  | Manufacturing / Engineering
JDE - RevRec |  | EMEA |  | Call Center
NE - CRM |  | APAC |  | Service Sales
NE - Customer Dashboard |  |  |  | Field Service
NE - Sales Hub |  |  |  | Marketing
NE - Post Award Field App |  |  |  | Finance
GSS - Sales |  |  |  | IT
GSS - FS/CC
Otis ONE - Multimedia
SVC - Customer Portal
Otis ONE - Data Solution
NE - Integrated Architect Asst.
NE - Otis.com

## formulas-don't change (hidden)
# | Beg | End | Beg | # | End | #
1 | 2018-01-01 | 2018-01-31 | 2018-01-01 | 1 | 2018-01-31 | 1
2 | 2018-02-01 | 2018-02-28 | 2018-02-01 | 2 | 2018-02-28 | 2
3 | 2018-03-01 | 2018-03-31 | 2018-03-01 | 3 | 2018-03-31 | 3
4 | 2018-04-01 | 2018-04-30 | 2018-04-01 | 4 | 2018-04-30 | 4
5 | 2018-05-01 | 2018-05-31 | 2018-05-01 | 5 | 2018-05-31 | 5
6 | 2018-06-01 | 2018-06-30 | 2018-06-01 | 6 | 2018-06-30 | 6
7 | 2018-07-01 | 2018-07-31 | 2018-07-01 | 7 | 2018-07-31 | 7
8 | 2018-08-01 | 2018-08-31 | 2018-08-01 | 8 | 2018-08-31 | 8
9 | 2018-09-01 | 2018-09-30 | 2018-09-01 | 9 | 2018-09-30 | 9
10 | 2018-10-01 | 2018-10-31 | 2018-10-01 | 10 | 2018-10-31 | 10
11 | 2018-11-01 | 2018-11-30 | 2018-11-01 | 11 | 2018-11-30 | 11
12 | 2018-12-01 | 2018-12-31 | 2018-12-01 | 12 | 2018-12-31 | 12
13 | 2019-01-01 | 2019-01-31 | 2019-01-01 | 13 | 2019-01-31 | 13
14 | 2019-02-01 | 2019-02-28 | 2019-02-01 | 14 | 2019-02-28 | 14
15 | 2019-03-01 | 2019-03-31 | 2019-03-01 | 15 | 2019-03-31 | 15
16 | 2019-04-01 | 2019-04-30 | 2019-04-01 | 16 | 2019-04-30 | 16
17 | 2019-05-01 | 2019-05-31 | 2019-05-01 | 17 | 2019-05-31 | 17
18 | 2019-06-01 | 2019-06-30 | 2019-06-01 | 18 | 2019-06-30 | 18
19 | 2019-07-01 | 2019-07-31 | 2019-07-01 | 19 | 2019-07-31 | 19
20 | 2019-08-01 | 2019-08-31 | 2019-08-01 | 20 | 2019-08-31 | 20
21 | 2019-09-01 | 2019-09-30 | 2019-09-01 | 21 | 2019-09-30 | 21
22 | 2019-10-01 | 2019-10-31 | 2019-10-01 | 22 | 2019-10-31 | 22
23 | 2019-11-01 | 2019-11-30 | 2019-11-01 | 23 | 2019-11-30 | 23
24 | 2019-12-01 | 2019-12-31 | 2019-12-01 | 24 | 2019-12-31 | 24
25 | 2020-01-01 | 2020-01-31 | 2020-01-01 | 25 | 2020-01-31 | 25
26 | 2020-02-01 | 2020-02-29 | 2020-02-01 | 26 | 2020-02-29 | 26
27 | 2020-03-01 | 2020-03-31 | 2020-03-01 | 27 | 2020-03-31 | 27
28 | 2020-04-01 | 2020-04-30 | 2020-04-01 | 28 | 2020-04-30 | 28
29 | 2020-05-01 | 2020-05-31 | 2020-05-01 | 29 | 2020-05-31 | 29
30 | 2020-06-01 | 2020-06-30 | 2020-06-01 | 30 | 2020-06-30 | 30
31 | 2020-07-01 | 2020-07-31 | 2020-07-01 | 31 | 2020-07-31 | 31
32 | 2020-08-01 | 2020-08-31 | 2020-08-01 | 32 | 2020-08-31 | 32
33 | 2020-09-01 | 2020-09-30 | 2020-09-01 | 33 | 2020-09-30 | 33
34 | 2020-10-01 | 2020-10-31 | 2020-10-01 | 34 | 2020-10-31 | 34
35 | 2020-11-01 | 2020-11-30 | 2020-11-01 | 35 | 2020-11-30 | 35
36 | 2020-12-01 | 2020-12-31 | 2020-12-01 | 36 | 2020-12-31 | 36
37 | 2021-01-01 | 2021-01-31 | 2021-01-01 | 37 | 2021-01-31 | 37
38 | 2021-02-01 | 2021-02-28 | 2021-02-01 | 38 | 2021-02-28 | 38
39 | 2021-03-01 | 2021-03-31 | 2021-03-01 | 39 | 2021-03-31 | 39
40 | 2021-04-01 | 2021-04-30 | 2021-04-01 | 40 | 2021-04-30 | 40
41 | 2021-05-01 | 2021-05-31 | 2021-05-01 | 41 | 2021-05-31 | 41
42 | 2021-06-01 | 2021-06-30 | 2021-06-01 | 42 | 2021-06-30 | 42
43 | 2021-07-01 | 2021-07-31 | 2021-07-01 | 43 | 2021-07-31 | 43
44 | 2021-08-01 | 2021-08-31 | 2021-08-01 | 44 | 2021-08-31 | 44
45 | 2021-09-01 | 2021-09-30 | 2021-09-01 | 45 | 2021-09-30 | 45
46 | 2021-10-01 | 2021-10-31 | 2021-10-01 | 46 | 2021-10-31 | 46
47 | 2021-11-01 | 2021-11-30 | 2021-11-01 | 47 | 2021-11-30 | 47
48 | 2021-12-01 | 2021-12-31 | 2021-12-01 | 48 | 2021-12-31 | 48
49 | 2022-01-01 | 2022-01-31 | 2022-01-01 | 49 | 2022-01-31 | 49
50 | 2022-02-01 | 2022-02-28 | 2022-02-01 | 50 | 2022-02-28 | 50
51 | 2022-03-01 | 2022-03-31 | 2022-03-01 | 51 | 2022-03-31 | 51
52 | 2022-04-01 | 2022-04-30 | 2022-04-01 | 52 | 2022-04-30 | 52
53 | 2022-05-01 | 2022-05-31 | 2022-05-01 | 53 | 2022-05-31 | 53
54 | 2022-06-01 | 2022-06-30 | 2022-06-01 | 54 | 2022-06-30 | 54
55 | 2022-07-01 | 2022-07-31 | 2022-07-01 | 55 | 2022-07-31 | 55
56 | 2022-08-01 | 2022-08-31 | 2022-08-01 | 56 | 2022-08-31 | 56
57 | 2022-09-01 | 2022-09-30 | 2022-09-01 | 57 | 2022-09-30 | 57
58 | 2022-10-01 | 2022-10-31 | 2022-10-01 | 58 | 2022-10-31 | 58
59 | 2022-11-01 | 2022-11-30 | 2022-11-01 | 59 | 2022-11-30 | 59
60 | 2022-12-01 | 2022-12-31 | 2022-12-01 | 60 | 2022-12-31 | 60
61 | 2023-01-01 | 2023-01-31 | 2023-01-01 | 61 | 2023-01-31 | 61
62 | 2023-02-01 | 2023-02-28 | 2023-02-01 | 62 | 2023-02-28 | 62
63 | 2023-03-01 | 2023-03-31 | 2023-03-01 | 63 | 2023-03-31 | 63
64 | 2023-04-01 | 2023-04-30 | 2023-04-01 | 64 | 2023-04-30 | 64
65 | 2023-05-01 | 2023-05-31 | 2023-05-01 | 65 | 2023-05-31 | 65
66 | 2023-06-01 | 2023-06-30 | 2023-06-01 | 66 | 2023-06-30 | 66
67 | 2023-07-01 | 2023-07-31 | 2023-07-01 | 67 | 2023-07-31 | 67
68 | 2023-08-01 | 2023-08-31 | 2023-08-01 | 68 | 2023-08-31 | 68
69 | 2023-09-01 | 2023-09-30 | 2023-09-01 | 69 | 2023-09-30 | 69
70 | 2023-10-01 | 2023-10-31 | 2023-10-01 | 70 | 2023-10-31 | 70
71 | 2023-11-01 | 2023-11-30 | 2023-11-01 | 71 | 2023-11-30 | 71
72 | 2023-12-01 | 2023-12-31 | 2023-12-01 | 72 | 2023-12-31 | 72