## Roadmap
Project | Region | Country | Resource1 | Resource2 | Start Date (dd/mm/yy) | End Date (dd/mm/yy)
JDE | Americas | Argentina | Fin |  | 2020-03-01 | 2020-09-30
JDE | EMEA | Austria | NES |  | 2018-11-01 | 2019-07-31
NE - CRM | APAC | Australia | IT |  | 2020-03-01 | 2020-03-31
NE - Customer Dashboard | APAC | Australia | Fserv |  | 2020-01-01 | 2020-12-31
JDE | EMEA | Belgium/Lux | Fsales |  | 2021-01-01 | 2021-08-31
Otis ONE - Data Solution | APAC | China | Fin |  | 2019-01-01 | 2019-05-31
Otis ONE - Data Solution | EMEA | France | NES |  | 2019-01-01 | 2019-05-31
JDE | EMEA | Bulgaria | IT |  | 2022-04-01 | 2022-12-31
Otis ONE - Data Solution | Americas | Otis NA | Fserv |  | 2019-03-01 | 2019-07-31
NE - Sales Hub | Americas | Brazil | Fsales |  | 2018-11-01 | 2019-03-31
JDE | EMEA | CEAM | Fin |  | 2020-01-01 | 2021-06-30
NE - Customer Dashboard | Americas | Canada | NES |  | 2020-01-01 | 2020-12-31
NE - Integrated Architect Asst. | Americas | Canada | IT |  | 2018-10-01 | 2019-06-30
JDE | Americas | Central America | Fserv |  | 2022-01-01 | 2022-06-30
JDE | Americas | Chile | Fsales |  | 2018-01-01 | 2018-09-30
JDE | Americas | Colombia | Fin |  | 2019-04-01 | 2020-01-31
JDE | EMEA | Cz Rep/Slovakia | NES |  | 2022-04-01 | 2022-12-31
JDE | EMEA | Denmark | IT |  | 2019-04-01 | 2019-09-30
Otis ONE - Multimedia | EMEA | Austria | Fserv |  | 2018-08-01 | 2019-02-28
Otis ONE - Multimedia | EMEA | Belgium | Fsales |  | 2019-05-01 | 2019-07-31
JDE | EMEA | Egypt | Fin |  | 2020-10-01 | 2021-06-30
JDE | EMEA | Estonia | NES |  | 2020-10-01 | 2021-03-31
JDE | APAC | Fiji/Samoa | IT |  | 2018-01-01 | 2018-07-31
JDE | EMEA | France | Fserv |  | 2021-01-01 | 2022-03-31
JDE | EMEA | France EPC | Fsales |  | 2019-02-01 | 2019-12-31
JDE | EMEA | Germany | Fin |  | 2019-07-01 | 2020-06-30
GSS - FS/CC | Americas | Otis NA | NES |  | 2019-05-01 | 2020-03-31
GSS - Sales | Americas | Otis NA | IT |  | 2018-09-01 | 2019-04-30
JDE | EMEA | Greece/Cyprus/Balkins | Fserv |  | 2022-02-01 | 2022-12-31
NE - Customer Dashboard | EMEA | France | Fsales |  | 2020-01-01 | 2020-12-31
NE - Integrated Architect Asst. | EMEA | France | Fin |  | 2018-10-01 | 2019-06-30
NE - Sales Hub | EMEA | France | NES |  | 2018-12-01 | 2019-06-30
Otis ONE - Multimedia | APAC | China | IT |  | 2018-11-01 | 2019-03-31
Otis ONE - Multimedia | EMEA | France | Fserv |  | 2018-08-01 | 2019-02-28
NE - CRM | EMEA | France | Fsales |  | 2020-01-01 | 2020-01-31
Otis ONE - Multimedia | EMEA | Germany | Fin |  | 2018-08-01 | 2019-02-28
JDE | APAC | Hong Kong | NES |  | 2018-01-01 | 2018-01-31
JDE | EMEA | Hungary | IT |  | 2022-04-01 | 2022-12-31
GSS - FS/CC | APAC | Hong Kong | Fserv |  | 2020-07-01 | 2020-12-31
GSS - Sales | APAC | Hong Kong | Fsales |  | 2019-07-01 | 2019-12-31
JDE | APAC | India | Fin |  | 2018-01-01 | 2018-07-31
NE - CRM | EMEA | Germany | NES |  | 2019-04-01 | 2019-12-31
NE - Customer Dashboard | EMEA | Germany | IT |  | 2020-01-01 | 2020-12-31
NE - Integrated Architect Asst. | EMEA | Germany | Fserv |  | 2018-10-01 | 2019-06-30
NE - Sales Hub | EMEA | Germany | Fsales |  | 2018-12-01 | 2019-06-30
Otis ONE - Multimedia | APAC | Hong Kong | Fin |  | 2018-08-01 | 2019-03-31
Otis ONE - Multimedia | APAC | Japan | NES |  | 2019-03-01 | 2019-05-31
JDE | EMEA | Italy | IT |  | 2020-07-01 | 2021-09-30
GSS - FS/CC | APAC | Japan | Fserv |  | 2021-01-01 | 2021-06-30
GSS - Sales | APAC | Japan | Fsales |  | 2020-07-01 | 2020-12-31
JDE | APAC | Japan | Fin |  | 2019-10-01 | 2020-10-31
JDE | APAC | Jpn/Schindler | NES |  | 2018-01-01 | 2018-03-31
NE - Integrated Architect Asst. | APAC | Hong Kong | IT |  | 2018-10-01 | 2019-06-30
Otis ONE - Multimedia | APAC | Korea | Fserv |  | 2019-03-01 | 2019-05-31
Otis ONE - Multimedia | EMEA | Luxemburg | Fsales |  | 2019-05-01 | 2019-07-31
Otis ONE - Multimedia | EMEA | Netherlands | Fin | Fserv | 2019-05-01 | 2019-07-31
JDE | EMEA | Kenya | NES | Fin | 2022-01-01 | 2022-08-31
JDE | APAC | Korea | IT | NES | 2018-08-01 | 2019-07-31
JDE | EMEA | Latvia | Fserv | IT | 2020-10-01 | 2021-03-31
NE - CRM | APAC | India | Fsales | Fserv | 2019-04-01 | 2019-12-31
NE - Customer Dashboard | APAC | India | Fin | Fsales | 2020-01-01 | 2020-12-31
NE - Sales Hub | APAC | India | NES | Fin | 2019-01-01 | 2019-03-31
JDE | APAC | Malaysia | IT | NES | 2018-01-01 | 2018-02-28
NE - Customer Dashboard | APAC | Indonesia | Fserv | IT | 2020-01-01 | 2020-12-31
NE - Integrated Architect Asst. | APAC | Indonesia | Fsales | Fserv | 2018-10-01 | 2019-06-30
GSS - FS/CC | APAC | Korea | Fin | Fsales | 2021-01-01 | 2021-06-30
GSS - Sales | APAC | Korea | NES | Fin | 2020-07-01 | 2020-12-31
JDE | EMEA | Netherlands | IT | NES | 2019-09-01 | 2020-07-31
NE - CRM | EMEA | Italy | Fserv | IT | 2020-06-01 | 2020-06-30
GSS - FS/CC | EMEA | France | Fsales | Fserv | 2020-07-01 | 2020-12-31
GSS - Sales | EMEA | France | Fin | Fsales | 2019-04-01 | 2019-09-30
JDE | APAC | OCL | NES | Fin | 2019-05-01 | 2020-06-30
Otis ONE - Multimedia | Americas | Otis NA | IT | NES | 2018-06-01 | 2019-02-28
JDE | Americas | OSC | Fserv | IT | 2020-05-01 | 2021-06-30
JDE | APAC | Otis Electric | Fin | Fserv | 2018-01-01 | 2019-01-31
JDE | Americas | Otis NA Ph.1/2/3 | NES | Fsales | 2018-01-01 | 2019-10-31
JDE | EMEA | Poland | IT | Fin | 2021-10-01 | 2022-08-31
GSS - FS/CC | EMEA | Germany | Fserv | NES | 2021-01-01 | 2021-06-30
GSS - Sales | EMEA | Germany | Fsales | IT | 2020-07-01 | 2020-12-31
JDE | EMEA | Portugal | Fin | Fserv | 2020-01-01 | 2020-10-31
NE - CRM | APAC | Korea | NES | Fsales | 2020-06-01 | 2020-06-30
NE - Customer Dashboard | APAC | Korea | IT | Fin | 2020-01-01 | 2020-12-31
NE - Sales Hub | APAC | Korea | Fserv | NES | 2019-04-01 | 2019-06-30
Otis ONE - Multimedia | EMEA | Portugal | Fsales | IT | 2019-07-01 | 2019-09-30
JDE | EMEA | Russia | Fin | Fserv | 2019-11-01 | 2020-10-31
Otis ONE - Multimedia | APAC | Singapore | NES | Fsales | 2018-08-01 | 2019-03-31
JDE | EMEA | Saudi Arabia/Bahrain | IT | Fin | 2019-10-01 | 2020-07-31
JDE | EMEA | South Africa | Fserv | NES | 2018-01-01 | 2018-01-31
NE - Customer Dashboard | APAC | Malaysia | Fsales | IT | 2020-01-01 | 2020-12-31
NE - Integrated Architect Asst. | APAC | Malaysia | Fin | Fserv | 2018-10-01 | 2019-06-30
JDE | EMEA | Spain | NES | Fsales | 2021-01-01 | 2022-05-31
NE - Customer Dashboard | Americas | Mexico | IT | Fin | 2020-01-01 | 2020-12-31
JDE | APAC | Supriya/TRIO | Fserv | NES | 2022-06-01 | 2022-12-31
JDE | EMEA | Sweden | Fsales | IT | 2020-11-01 | 2021-08-31
NE - CRM | Americas | NAA | Fin | Fserv | 2019-07-01 | 2019-12-31
NE - Sales Hub | Americas | NAA | NES | Fsales | 2018-11-01 | 2018-12-31
JDE | EMEA | Switzerland | IT | Fin | 2020-01-01 | 2020-10-31
Otis ONE - Multimedia | EMEA | Spain | Fserv | NES | 2019-03-01 | 2019-05-31
JDE | APAC | Taiwan | Fsales | IT | 2019-03-01 | 2019-11-30
JDE | EMEA | UAE/Qatar/MET | Fin | Fserv | 2019-03-01 | 2019-11-30
NE - CRM | APAC | OCL | NES | Fsales | 2020-07-01 | 2021-03-31
NE - Sales Hub | APAC | OCL | IT | Fin | 2018-12-01 | 2019-01-31
NE - Integrated Architect Asst. | APAC | OCL | Fserv | NES | 2018-10-01 | 2019-06-30
JDE | EMEA | UK & Ireland | Fsales | IT | 2019-04-01 | 2020-03-31
JDE | EMEA | Ukraine | Fin | Fserv | 2020-07-01 | 2020-12-31
NE - CRM | APAC | Otis Electric | NES | Fsales | 2020-07-01 | 2021-03-31
NE - Sales Hub | APAC | Otis Electric | IT | Fin | 2019-01-01 | 2019-03-31
Otis ONE - Multimedia | EMEA | Switzerland | Fserv | NES | 2019-07-01 | 2019-09-30
GSS - FS/CC | EMEA | Italy | Fsales | IT | 2021-01-01 | 2021-06-30
GSS - Sales | EMEA | Italy | Fin | Fserv | 2020-07-01 | 2020-12-31
NE - Customer Dashboard | Americas | Otis NA | NES | Fsales | 2019-01-01 | 2019-12-31
Otis ONE - Multimedia | EMEA | UK | IT | Fin | 2019-03-01 | 2019-05-31
SVC - Customer Portal | EMEA | Austria (ONE Pilots) | Fserv | NES | 2018-12-01 | 2018-12-31
NE - Integrated Architect Asst. | Americas | Otis NA | Fsales | IT | 2018-10-01 | 2019-06-30
SVC - Customer Portal | EMEA | France (ONE Pilots) | Fin | Fserv | 2018-12-01 | 2018-12-31
NE - CRM | Americas | Otis NA - Dallas | NES | Fsales | 2019-04-01 | 2019-06-30
NE - CRM | Americas | Otis NA - Fort Worth | IT | Fin | 2019-04-01 | 2019-06-30
SVC - Customer Portal | EMEA | Germany (ONE Pilots) | Fserv | NES | 2018-12-01 | 2018-12-31
NE - CRM | Americas | Otis NA - Washington D.C. | Fsales | IT | 2019-04-01 | 2019-06-30
SVC - Customer Portal | APAC | Hong Kong (ONE Pilots) | Fin | Fserv | 2018-11-01 | 2018-11-30
JDE - RevRec | Americas | Chile | NES | Fsales | 2020-05-01 | 2020-09-30
JDE - RevRec | Americas | Mexico | IT | Fin | 2018-07-01 | 2018-10-31
GSS - Sales | EMEA | Portugal | Fserv | NES | 2018-09-01 | 2019-04-30
JDE - RevRec | Americas | NAA | Fsales | IT | 2018-10-01 | 2019-03-31
GSS - FS/CC | EMEA | Portugal | Fin | Fserv | 2020-01-01 | 2020-06-30
JDE - RevRec | Americas | Uruguay | NES | Fsales | 2020-05-01 | 2020-09-30
JDE - RevRec | APAC | Australasia | IT | Fin | 2019-08-01 | 2019-12-31
NE - CRM | EMEA | Russia | Fserv | NES | 2020-04-01 | 2020-04-30
JDE - RevRec | APAC | China | Fsales | IT | 2018-10-01 | 2019-02-28
NE - CRM | APAC | SE Asia | Fin | Fserv | 2020-02-01 | 2020-02-29
NE - Sales Hub | APAC | SE Asia | NES | Fsales | 2019-04-01 | 2019-06-30
JDE - RevRec | APAC | Hong Kong | IT | Fin | 2019-08-01 | 2019-12-31
NE - Customer Dashboard | APAC | Singapore | Fserv | NES | 2020-01-01 | 2020-12-31
NE - Integrated Architect Asst. | APAC | Singapore | Fsales | IT | 2018-10-01 | 2019-06-30
SVC - Customer Portal | APAC | Otis Electric (ONE Pilots) | Fin | Fserv | 2018-12-01 | 2018-12-31
JDE - RevRec | APAC | India | NES | Fsales | 2019-03-01 | 2019-08-31
JDE - RevRec | APAC | Indonesia | IT | Fin | 2019-12-01 | 2020-04-30
GSS - FS/CC | EMEA | Spain | Fserv | NES | 2020-01-01 | 2020-06-30
GSS - Sales | EMEA | Spain | Fsales | IT | 2019-04-01 | 2019-09-30
JDE - RevRec | APAC | Jpn/Schindler | Fin | Fserv | 2019-08-01 | 2019-12-31
NE - CRM | EMEA | Spain | NES | Fsales | 2020-02-01 | 2020-02-29
NE - Customer Dashboard | EMEA | Spain | IT | Fin | 2020-01-01 | 2020-12-31
NE - Sales Hub | EMEA | Spain | Fserv | NES | 2018-12-01 | 2019-06-30
SVC - Customer Portal | Americas | Otis NA - One Pilots | Fsales | IT | 2018-12-01 | 2018-12-31
JDE - RevRec | APAC | Malaysia | Fin | Fserv | 2019-08-01 | 2019-12-31
JDE - RevRec | APAC | Singapore | NES | Fsales | 2019-03-01 | 2019-08-31
GSS - FS/CC | EMEA | Switzerland | IT | Fin | 2020-01-01 | 2020-06-30
GSS - Sales | EMEA | Switzerland | Fserv |  | 2018-09-01 | 2019-04-30
JDE - RevRec | APAC | Thailand | Fsales |  | 2019-12-01 | 2020-04-30
SVC - Customer Portal | Americas | Otis NA - West Palm Beach | Fin |  | 2018-11-01 | 2018-11-30
JDE - RevRec | APAC | Vietnam | NES |  | 2019-12-01 | 2020-04-30
NE - Integrated Architect Asst. | APAC | Taiwan | IT |  | 2018-10-01 | 2019-06-30
JDE - RevRec | EMEA | Finland | Fserv |  | 2019-12-01 | 2020-05-31
NE - Customer Dashboard | APAC | Thailand | Fsales |  | 2020-01-01 | 2020-12-31
NE - Integrated Architect Asst. | APAC | Thailand | Fin |  | 2018-10-01 | 2019-06-30
JDE - RevRec | EMEA | Knutsen | NES |  | 2019-12-01 | 2020-05-31
NE - CRM | EMEA | Turkey | IT |  | 2019-04-01 | 2019-06-30
JDE - RevRec | EMEA | Morocco | Fserv |  | 2020-04-01 | 2020-09-30
GSS - FS/CC | EMEA | UK | Fsales |  | 2021-01-01 | 2021-06-30
GSS - Sales | EMEA | UK | Fin |  | 2020-07-01 | 2020-12-31
NE - CRM | EMEA | UK | NES |  | 2021-05-01 | 2021-05-31
NE - Customer Dashboard | EMEA | UK | IT |  | 2020-01-01 | 2020-12-31
NE - Integrated Architect Asst. | EMEA | UK | Fserv |  | 2018-10-01 | 2019-06-30
SVC - Customer Portal | APAC | Singapore (ONE Pilots) | Fsales |  | 2018-12-01 | 2018-12-31
JDE - RevRec | EMEA | Norway | Fin |  | 2019-12-01 | 2020-05-31
JDE - RevRec | EMEA | Romania | NES |  | 2020-04-01 | 2020-09-30
JDE - RevRec | EMEA | South Africa | IT |  | 2019-12-01 | 2020-05-31
JDE - RevRec | EMEA | Turkey | Fserv |  | 2020-04-01 | 2020-09-30
NE - Customer Dashboard | APAC | Vietnam | Fsales |  | 2020-01-01 | 2020-12-31
NE - Post Award Field App | Americas | NAA | Fin |  | 2019-01-01 | 2019-09-30
NE - Post Award Field App | APAC | Australia | NES |  | 2019-04-01 | 2019-12-31
NE - Post Award Field App | APAC | India | IT |  | 2019-04-01 | 2019-12-31
NE - Post Award Field App | APAC | Korea | Fserv |  | 2019-04-01 | 2019-12-31
NE - Post Award Field App | APAC | SE Asia | Fsales |  | 2019-04-01 | 2019-12-31
NE - Post Award Field App | EMEA | France | Fin |  | 2019-01-01 | 2019-09-30
NE - Post Award Field App | EMEA | Germany | NES |  | 2019-01-01 | 2019-09-30
NE - Post Award Field App | EMEA | Spain | IT |  | 2019-01-01 | 2019-09-30
NE - Post Award Field App | EMEA | UK | Fserv |  | 2019-01-01 | 2019-09-30
NE - Otis.com | EMEA | Turkey | Fsales |  | 2018-09-01 | 2018-10-31
NE - Otis.com | EMEA | EMEA All | Fin |  | 2018-10-01 | 2018-12-31
NE - Otis.com | APAC | Hong Kong | NES |  | 2018-10-01 | 2018-11-30
NE - Otis.com | APAC | Japan | IT |  | 2018-09-01 | 2018-10-31
NE - Otis.com | APAC | Taiwan | Fserv |  | 2018-10-01 | 2018-11-30
NE - Otis.com | Americas | Latin America | Fsales |  | 2018-09-01 | 2018-10-31

## Color
Project | Project Code | Region | Region Code | Resource | Resource code
JDE |  | Americas |  | Manufacturing/Engineering
JDE – RevRec |  | EMEA |  | Call Center
NE – CRM |  | APAC |  | Service Sales
NE - Customer Dashboard |  |  |  | Field Service
NE - Sales Hub |  |  |  | Marketing
NE - Post Award Field App |  |  |  | Finance
GSS – Sales |  |  |  | IT
GSS - FS/CC |  |  |  | Fin
Otis ONE – Multimedia |  |  |  | NES
SVC - Customer Portal
Otis ONE - Data Solution
NE - Integrated Architect Asst.
NE - Otis.com